| **No.** | **Duration****(3years)****6/2018-7/2021** | **Activities** | **Participants** |
| --- | --- | --- | --- |
| 1 | 6/2018-12/2019 | Set up plan for project – 1.5 years- The project plan proposal needs to be approved by project organisation.- Preparing media system to set up for next steps.- Contacting women’s associations in Hue region to receive permission in conducting the project survey.- Preparing training materials.- Preparing conference to show the benefits of the project to authorities in local areas.- Every local area, set up a team project leader to manage staff. | Project team |
| 2 | 1/2020-3/2020 | Volunteer recruitment (3months)- The announcement to recruit volunteers studying with different majors are through all college.- All potential volunteers will be interviewed for this project, approximately 50 volunteers are chosen. | Project team |
| 3 | 4/2020-6/2020 | Volunteer training – 3 monthsThere are three workshops during volunteer trainingWorkshop 1: Collecting survey data method, approaching high school students’ ideology of domestic violence against women.In this workshop, volunteers will be guided on how to collect and analyse survey data. Besides, they will be learnt how to approach high school students’ ideology by psychologist experts.Workshop 2: Skills and work in teamworkProject skill focuses on building and increasing high school students’ ideology regarding domestic violence against women. Therefore, volunteers will be trained on how to work with students between the age of 13-17. There are other skills such as presentation skill, animator skill. Also, this workshop will guide volunteer how to work in teamwork.Workshop 3: Writing report skill and ethical considerationVolunteers will be learnt how to write the report by project team leader.There are some sensitive languages of gender need to mention to make sure volunteers can avoid. | Lecturers, volunteers |
| 4 | 7/2020-10/2020 | Conducting survey – 3 monthsIt will take one month for volunteers collecting data from women in Hue area. Other two months will spend for collecting result to see the context of society regarding against women in their local area. | volunteers, women in local area.(household, market,women union of ward..etc.) |
| 5 | 10/2020-11/2020 | Expert talk show – 1 monthEvery talk show with expert, high school students have chances to discuss and listen to some stories and experts’ experiences about violence against women and domestic violence against women. There are some touching stories will be given helping students’ awareness about their role in society for anti-violence women. | Lecturers, volunteers, women in local area.(household, market,women union of ward..etc.)., expert  |
| 6 | 11/2020-3/2021 | Training workshop – 4 monthsThere are five workshops with some sub-workshops will be organised for five months. In this time, teachers are encouraged to cooperate with volunteers for guiding high school students’ ideology about the role of women in society. Furthermore, secondary students’ role also mentioned seeing how their contribution to society by saying no violence to women. | Lecturers, volunteers, women in local area.(household, market,women union of ward..etc.)., expert |
|  | 3/2021-4/2021 | Case studies – 1 monthThere are some suggested situations given to high school students and require them to handle it. In this time, students will be learnt which organisation they should contact if domestic violence is happening in their local areas. Additionally, they will know how to protect their female relatives under domestic violence by connecting authority. Regarding female students, they will know how to protect themselves in the future if violence happens. | Lecturers, volunteers, women in local area.(household, market,women union of ward..etc.) |
|  | 4/2021-5/2021 | Evaluation time and sending report – 1monthIn this time, volunteers and teachers will test secondary students via survey and some question tests. Besides, evaluation time is a good time for the student can discuss openly with volunteers and teachers, as well they can share their thinking about domestic violence happened to women. After that, volunteers will write down the final report of the current year and send to project organisation. | Lecturers, volunteers |
|  | 5/2021-7/2021 | Project evaluation (2 months)Project evaluation will be implemented within three years of the project. There are some surveys will send to the volunteers through their email. The evaluation will concentrate on the sustainability of the project, the results and constraints of the project. | Lecturers, volunteers |